## Sheet1
Module | Function | Status
Login
| check supplied password against db password | done
| check that supplied user exists | done
| use encryption for passwords | pending
Clients
list clients trades
| view deal note from client trades | duplicating deal note display
| reverse deal | pending
| post new deal link | done
| new client link | pending
| create new client | pending
Front Office
| capture new deal (only cliet deal is captured) | done
| view deal allocations - filter by deal date | done
| print daybook | done - pending finalization
| print selected deal(s) | done
| print all deals | done
Transactions
New transaction
Approve payment
| Review payments | pending
| Review receipts | pending
| Post New tax payment requisition | done
| List tax requisition in payments for approval | pending
Reports
| View ledger report | pending - only displaying CSD txns for any ledger selected
| Client Statement | not filtering according to eriod specified by date range
Admin
| list system users | done
| reset password | pending
| lock/unlock user | pending
| change user profile | pending
| add new user | pending